## Slide 2: eduroam Roadmap – Complete Timeline Overview
[ops] eduroam db ver 2.0: 2019-01 – 2020-02
[ops] eduroam audit: 2019-04 – 2020-11
[ops] eduroam documentation: 2019-01 - 2020-12
[ops] Continuos maintenance & deploment of improvements : 2019-01 – 2022-12
[dev] eduroam Managed SP: 2019-01 – 2021-06
[dev] eduPKI certificate provisioning redesign: 2019-06 - 2020-06
[dev] Additional building blocks for end-user diagnostics: 2019-06 – 2020-10
[dev] radsecproxy SW development: 2019-01 – 2020-12
[dev] Continuous service improvements: 2019-01 – 2020-12

## Slide 3: eduroam Operations and Deployment Roadmap
eduroam Database v2.0
2019
Q3
Q1
Q2
Q3
Q1
Q2
2020
Q4
Q4
Align eduroam db access tools with eduroam db v2.0
Tools prepared
New features deployed to the monitor site
Draft the audit procedure and prepare the accomplying tools
Pilot with European NRENs
Summarize pilot results and conclude the final procedure with SG and GeGC
Perform first NRO audit (repeats annually)
eduroam Audit
Collect the proposals for the new Policy from stakeholders
Prepare draft of the new Policy
Consultation period with the SG, finalize the Policy update
eduroam Policy Update
Migration to the eduroam db v2.0
Continuous Operations, Support and Deployment of Enhancements
Signing of the new Policy by the European eduroam members

## Slide 4: eduroam Operations and Deployment Roadmap Work Item: eduroam db - Timeline
2019-01 : ongoing migration to eduroam db ver.2.0
2019-11 : end migration to eduroam db ver.2.0
2019-12 : eduroam db access tools import/export data aligned only with v2.0 format
2020-02 : released new features on monitor.eduroam.org (based on newly added data in eduroam db ver.2.0 format)

## Slide 5: eduroam Operations and Deployment Roadmap Work Item: eduroam audit - Timeline
2019-04 : work started
2019-08 : draft procedure and accompanying tools ready
2019-10 : NRO pilot audit (on European NROs) started
2019-12 : NRO pilot audit ends
2020-06 : audit docs and pilot results discussed with SG and GeGC – final version accepted
2020-09: first official NRO audit started (to be repeated annualy)
2020-11: first official NRO audit ended (results published)

## Slide 6: eduroam Operations and Deployment Roadmap Work Item: eduroam documentation - Timeline
2019-01 : start collecting proposals for Policy change
2019-06 : draft proposal for new wiki.eduroam.org
2019-12 : first draft of the new Policy
2019-12 : new wiki structure and content available
2019-06 : new Policy accepted by the SG, ready for signing
2020-12 : end of signing new Policy process

## Slide 7: eduroam Development Roadmap
2019
Q3
Q1
Q2
Q3
Q1
Q2
2020
Q4
Q4
Q1
Q2
2021
eduroam Managed SP
Certificate Provisioning Redesign (eduPKI)
End-user Diagnostics
Radsecproxy
Development
Technical development work
Implement the service prototype
Prepare for the PLM approved pilot
Run the service pilot
Technical development and policy change
Improve user communication
Testing new system
Deploy in CAT
Integrate hardware probes, F-ticks and eduroam db 2.0. Deploy in CAT
Code Rewrite radsecproxy V1.8
DNS radsecproxy V1.9
Load-balancing and pooling radsecproxy V2.0
Systemd inegration radsecproxy V2.1
Tranistion of the service for production
Service in production
Prototype hardware probe available
Access to F-ticks and db 2.0 available
Continuous Service Improvements

## Slide 8: eduroam Development Roadmap Work Item: eduroam Managed SP - Timeline
2019-01 : start of technical development work
2019-06 : running prototype
2019-12 : product ready for pilot on the technical side
2020-06 : start of PLM-approved pilot
2020-12 : preparations for transition to service
2021-06 : system in production service (coinciding with CAT software release 2.1)

## Slide 9: eduroam Development Roadmap Work Item: eduPKI certificate provisioning redesign - Timeline
2019-06 : start of technical development work and policy change process
2019-12 : system ready for testing
2020-06 : functionality available in CAT 2.0.x

## Slide 10: eduroam Development Roadmap Work Item: additional building blocks for end-user diagnostics - Timeline
2019-06 : start work on improvements to user communications (actionable insights) with dataset available in eduroam DB v1
2019-10 : first (prototype) hardware probe available, start work on integration of probes into diagnostics framework
2019-11 : world-wide deadline for eduroam DB v2 upgrade
2019-12 : access to F-Ticks real-time feed available, eduroam DB data v2 available
2020-10 : hardware probes, F-Ticks, eduroam DB v2 fully integrated, code available in aCAT 2.0.x release

## Slide 11: eduroam Development Roadmap Work Item: radsecproxy software development - Timeline
2019-06: rewrite (radsecproxy 1.8)
2019-12: DNS (radsecprox 1.9)
2020-07: load-balancing and pooling (radsecproxy 2.0)
2020-12: systemd integration (radsecproxy 2.1)