# SCHAC Project  Plan

Document information

Author:	Licia Florio

Version:	1.2

Date:		6 June 2014

Status:	For approval

Content

1	Introduction and Motivations								1

2	Project goals										2

3	Project duration										2

4	Project Plan and Deliverables							2

5	Project costs										3

6	Project budget and financing								4

7	Project participants									4

8	Project reporting										4

# Introduction and Motivations

The Schema for Academia (SCHAC) was launched in 2005 as result of work carried out in the area of attribute coordination to address inter-institutional data exchange.

SCHAC was initially operated as a community effort and led by TERENA. Later on it was agreed to formalize SCHAC; Victoriano Giralt (UMA) and Javier Masa (RedIRIS) led most of the work. Over the last few years, both Victoriano Giralt’s and Javier Masa’s involvement became very marginal, which caused SCHAC to fall into a state of disrepair.

Although the REFEDS-SC agreed to host SCHAC and ensure its operations in the future, the REFEDS-SC feel that it is not REFEDS responsibility to repair SCHAC.

The situation is such that either TERENA must bring SCHAC on track or the schema will have to be abandoned. Given the number of institutions and NRENs that have indicated they are using SCHAC, there is a push to have TERENA provide the leadership to bring SCHAC up to date.

With the world of federation and Internet identity growing at a rapid pace, having a well-structured and maintained attribute schema for academia is critical for efficient federation and interfederation interoperability.

# Project goals

Experts in the field have analysed SCHAC and identified a number of actions (a total of nine) to bring SCHAC into a functioning attribute schema.

The complete list is online at: https://refeds.terena.org/index.php/SCHAC_Plan

The aim of this project is to harmonise all the SCHAC-related documentation and tools currently available in the TERENA website into one single SCHAC specification.

The outcome of the work will be a coherent SCHAC schema and appropriate documentation on the TERENA’s wiki, and the creation of a SCHAC editorial board.

# Project duration

The  project runs from August 2014 until December 2014.

# Project Plan and Deliverables

The project will be carried out as indicated below:

- Task 1 – Review the existing SCHAC documentation to update the namespace: the original namespace urn:mace:terena.org:schac was deprecated in 2011 in favour of urn:schac. This has not been reflected into the SCHAC documents (see http://www.terena.org/activities/tf-emc2/schacreleases.html)

Deadline: End Oct 2014

- Task 2- Discuss whether the SCHAC attribute definition page should be updated (http://www.terena.org/registry/terena.org/attribute-def/ ) to list OID instead than URN or deleted completely and replaced with a link to the SCHAC new specification document to be written.

Deadline: End Oct 2014

- Task 3 – Harmonise the registry used for SCHAC – to date TERENA runs two registries in parallel:

- a static html registry: http://www.terena.org/registry/terena.org/

- and registry tool: https://urnreg.terena.org/browser/ (this one also used to manage TERENA OIDs)

Note that the two registries also use different OIDs (1.3.6.1.4.1.25178.1.1 and 1.3.6.1.4.1.25178.1.2)

A decision should be taken as to which registry to use, if any at all.

Deadline: End Nov 2014

- Task 4 – Establish SCHAC editorial board and its governance (this should be a very light weighted approach)

Deadline: Oct 2014

- Task 5- Move all existing documentation (SCHAC specifications PDF and SCHAC LDAP Schema) into one single authoritative SCHAC specification containing all the necessary information.  The TERENA federated wiki would be a good place for this.

Deadline: Dec 2014

This project will have two deliverables:

D1: SCHAC schema and appropriate documentation to be available on the TERENA’s wiki (Dec 2014)

D2: Creation of a SCHAC editorial board (Oct 2014)

# Project costs

The project will be carried out by Heather Flanagan,  an independent contractor.

| Task | Estimated Effort | Estimated Cost |
| --- | --- | --- |
| Task 1 | 4 days | 800 Eur |
| Task 2 | 7 days | 1400 Eur |
| Task 3 | 10 days | 2000 Eur |
| Task 4 | 4 days | 800 Eur |
| Task 5 | 10 days | 2000 Eur |
| Travel costs to attend REFEDS Meeting to report on the work | 3 days | 600+ max of 1500 travel costs |
| TOT | 35 days | 9100 EUR |

# Project budget and financing

At this point in time, there is no capacity in TERENA to carry out this work which could be quite time consuming. A SCHAC Shepherd (Heather Flanagan) has been found to work on this project.

The project requires EUR 7.000 to pay the contractor for executing the activities described under “Project Plan and Deliverables”.

TERENA is asked to fund this work.

# Project participants

Prior to this document NRENs have been asked to step forward to create a SCHAC editorial board that would provide feebadck to this work.

A number of NRENs have already volunteered namely: GARR, FUNET, ACONET, UNINETT, CANARIE  and I2. A mailing list will be created as soon as this project is approved.

This editorial board will also remain in place to define a governance model for SCHAC. This work is however out of scope for this project and will be only carried out (with the REFEDS budget) once the work in the project is concluded.

# Project reporting

The contractor will report per email to Licia Florio about the progresses of the work.

The progresses of the project will be communicated to the community at large during various events such as REFEDS meetings.

TERENA runs the OIDs for eduroam and TCS as well.

The acutal publishing of the content on the wiki will be done by TERENA.

The next possible REFEDS meeting would be the one organised at TNC. The costs are calcualted on the assumption of a flight from Seattle.