## ProjPlanServiceTransit_Template
Week | EC | SA5 Internal | Key SA5 other task dates | Key SA4 dates | Communication intiated by TL | PMF Deliverable | PLM Deliverable | Other
Week 1 |  | - Confirm team members (Services Team and SA4), key stakeholders and email addresses/contact details - Confirm/define objectives and timescale with key stakekolders - Set-up email distribution list - Set-up Wiki workspace |  |  | Phone/Email/Skype
Week 2 |  | Set-up foodle on date for two kick-off meetings with:- 1. Services Team plus key stakholder 2. SA4 and Services Team plus key stakeholder |  |  | Email
Week 3 |  | -Await feedback from Doodle - Complete email distribution list - Complete set-up of Wiki workspace - Ensure all team members have access to relevant systems/sites
Week 4 |  | - Schedule two kick-off meetings with:- 1. Services Team plus key stakholder 2. SA4 and Services Team plus key stakeholder -> Introduce Team and Timelines -> Introduce Service Transisition Inititation Template -> Agree on environment, process and acceptance criteria and understand specification within SA4 -> Agree weekly/biweekly calls |  |  | - VC with SA4 and Services Team - VC with Services Team | RAG Report TL to AL
Week 5 |  | Team and key stakeholder to review/complete Service Transisition Initiation Template [4 weeks] w1 |  | Team and key stakeholder to review/complete Service Transisition Initiation Template [4 weeks] w1
Week 6 |  | Team and key stakeholder to review/complete Service Transisition Initiation Template [4 weeks] w2 | Set-up foodle for two follow-up meetings with: 1. Services Team 2. SA4 and Services Team | Team and key stakeholder to review/complete Service Transisition Initiation Template [4 weeks] w2 | Call / email team
Week 7 |  | Team and key stakeholder to review/complete Service Transisition Initiation Template [4 weeks] w3 | Await feedback on two foodle/dates | Team and key stakeholder to review/complete Service Transisition Initiation Template [4 weeks] w3 | Email/Phone
Week 8 |  | Team and key stakeholder to review/complete Service Transisition Initiation Template [4 weeks] w4 | Schedule two follow-up meetings with: 1. Services Team 2. SA4 and Services Team | Team and key stakeholder to review/complete Service Transisition Initiation Template [4 weeks] w4 | Call / email team | RAG Report TL to AL
Week 9 |  | Hold Follow-up meetings to discuss/review filled-in Service Transisition Initiation Template with:- 1. Services Team and 2. SA4 and Services Team |  |  | - VC with SA4 and Services Team - VC with Services Team
Week 10 |  | Provision requirements |  |  | Weekly calls
Week 11 |  | Provision requirements |  |  | Weekly calls
Week 12 |  | Provision requirements |  |  | Weekly calls | RAG Report TL to AL
Week 13 |  |  |  | SA4T1 and T2 Service Valdiation & Testing (8 weeks) w1 | Weekly calls |  |  | Over the 8 weeks: - SA4T1 Service Validation [Software quality check] - SA4T2 Service Operation (Operation) [validate documentation and service fit for production]
Week 14 |  |  |  | SA4T1 and T2 Service Valdiation & Testing (8 weeks) w2 | Weekly calls
Week 15 |  |  |  | SA4T1 and T2 Service Valdiation & Testing (8 weeks) w3 | Weekly calls
Week 16 |  |  |  | SA4T1 and T2 Service Valdiation & Testing (8 weeks) w4 | Weekly calls | RAG Report TL to AL
Week 17 |  |  |  | SA4T1 and T2 Service Valdiation & Testing (8 weeks) w5 | Weekly calls
Week 18 |  |  |  | SA4T1 and T2 Service Valdiation & Testing (8 weeks) w6 | Weekly calls
Week 19 |  |  |  | SA4T1 and T2 Service Valdiation & Testing (8 weeks) w7 | Weekly calls
Week 20 |  |  |  | SA4T1 and T2 Service Valdiation & Testing (8 weeks) w8 | Weekly calls | RAG Report TL to AL
Week 21 |  |  |  | SA4T2 Service Continuity [3 weeks] w1 | Weekly calls
Week 22 |  |  |  | SA4T2 Service Continuity [3 weeks] w2 | Weekly calls
Week 23 |  |  |  | SA4T2 Service Continuity [3 weeks] w3 | Weekly calls
Week 24 |  | Review |  |  |  | RAG Report TL to AL
…
Week xxx minus 6 weeks |  | Deliverable due to send to Technical Authors/QASPER |  |  | Email
Week xxx | Deliverable due to be sent to EC through Technical Authors
Week yyy |  | Lessons Learnt
Week zzz |  | Celebrations