## Slide 1: Kick-Off GN5-1 WP5 T7
Project Participants Sensitive (SEN)
04&05 December 2023
(text in red: be warned, nothing but the opinion of Christoph needing validation)
(amendments in green: feedbacks from the meeting of 4 Dec)
Distributed Identities
Christoph Graf, Switch
Tasklead GN5-1 WP5 T7

## Slide 2
Paul can we have an agenda slide?
Expectations/Intros (see our wiki with your inputs)
Scoping our task
Proposed work plan
Collaboration (tooling, scheduling, etc.)
Administrivia (FTEs, etc.)
Next steps
Agenda

## Slide 3: Round-table introductions
A couple of sentences on:
  Who you are
  Your affiliation
  Your interest in the topic
  What you might want to contribute
amineh.akhavan-saraf@lrz.de | Amineh Akhavan Saraf
christoph.graf@switch.ch | Christoph Graf
hardt@kit.edu | Marcus Hardt
maarten.kremers@surf.nl | Maarten Kremers
marina@sunet.se | Marina Adomeit
mohacsi.janos@kifu.gov.hu | János Mohácsi
niels.vandijk@surf.nl | Niels van Dijk
nliam@grnet.gr | Nicolas Liampotis
pempe@dfn.de | Wolfgang Pempe
ruiz_ben@dfn.de | Esther Ruiz Ben
slavek@ics.muni.cz | Slávek Licehammer
See also: https://wiki.geant.org/display/GWP5/Who%27s+who+-+quick+intro

## Slide 4: Scoping our task
A number of ”dimensions” to look into
  A look at our Task in the Tech Annex of GN5-1
  Embedding SSI in our IDM big picture: why bother?
  Ripeness considerations: where to engage?
  SSI functional blocks: areas of interest?
  ToIP thematic fields: technical and/or governance?
  The USPs of GÉANT: where are we needed?
  What will our contribution be?

## Slide 5: Our Task in the Tech Annex of GN5-1
WP5 (excerpt about T7): […] In the first project period [i.e. 2023], the team will investigate distributed technologies and sovereign identities that have been identified as a key priority by the GÉANT community, with the aim to fit some activities in this area in the work plan for the second project period. […]
Task 7: Distributed Identities (Task Leader: Christoph Graf – SWITCH)
There has recently been a strong movement to make the whole identity space more user-centric to allow users greater control of their identities (and other related information) and a more active role in the process of sharing their information with other parties.
This task will explore the use cases that would be better supported via distributed technologies and the implications on the current services and infrastructure used in the R&E community. Starting at M6 of the project, Task 7 will:
Review existing services to identify opportunities and challenges to adopt the distributed technologies paradigm.
Gather previous work done by the NRENs/universities on using SSI technologies, as well as other sectors.
Investigate implementation of distributed identities use cases and pilot them with the broader community and assess impacts and technological readiness.
Establish a communication channel with relevant existing initiatives in the NRENs and beyond (i.e., EBSI).
See: https://geantprojects.sharepoint.com/:b:/s/gn5-1wp1/ERCbd1W7ia5KnYD-Lr37ztgBJ6uwwrS7GlGhEOZvSDl5LA?e=bSh0WK

## Slide 6: Scoping: IDM trends, how we look at SSI
t
Service
centric
Org-
centric
federated
Inter-
federated
User-centric
National AAIs
eduGAIN
SSI
National edu-IDs
??
«Next big thing» in IDM-world
Or disastrous fail (both considered equally likely to happen)
Better use Distributed Identities instead of SSI

## Slide 7: Scoping: Ripeness considerations and proposed positioning
t
Demos
(Click dummies/ Real tools, personas)
Approach
Ambition
Stakeholders get the idea
Pilots
(Real tools, real users, time limited)
Learning, users feel the future
MVP (Real tools, real users, start small but extensible)
Engage users, add value & grow
Production/DevOps
Decide on our role and what to trial and what to bring into production
Many players active, decide where to participate
Service
Potential positioning
There exists a lifecycle model in GEANT, but we prefer not to use it here for simplicity reasons

## Slide 8: Scoping: SSI functional blocks
decentralized trust network
Issuer
Verifier
authorithy
Holder
VC Verifiable Credentials
VC
Proof
DID
verification
DID
verification
technical scheme
registration
registration
DID Decentralized Identifiers
Conditions of participation
Rules of conduct
Remuneration models
Roles & Responsibilities
Detection quality
Data Protection & Privacy
Governance
Framework
Proof of Credentials
verification
Proposed positioning: concentrate on areas we have a strong footprint already:
Exchange of data between organisations
Standardise protocols, formats & semantics
Set up governance for our sector
Probably not much on the wallet, as this is likely organised cross-sectorial
Monitor EUDI Wallet for fit with our use cases
Source: DIDAS.ch
Remark: get the wording right, wording is framing, decouple from ledgers. Shall we use «decentral identities» to replace «SSI»? Repaint with «our» use cases. Refer to OIDC-federation PoC as trust fabric.
Wallet: member states will need to provide a EUDI Wallet, but we do not yet know the rules attached to it. We should monitor this field and check whether those wallets underpin our use cases. Repaint picture with the terminology we support.

## Slide 9: Scoping: technical and or governance (Trust over IP)
Proposed positioning: Top candidates are the fields we are already active in, e.g. eduGAIN, Refeds and co.:
Layer 3 and 4 for the international NREN ecosystem
Re-use the established governance structures in the emerging SSI-ecosystem
Layer 2: Monitor the development of the protocols (mDoc and OID4VC) - similarities to what we have at the moment increased
Layer 1: we should strive for decentralising the trust framework (not just on the "ledger layer”) for the benefit of research infrastructures/projects

## Slide 10: Scoping: The USPs of GÉANT
Track record of setting technical and governance standards for the federated identity and access management framework in the academic and research community worldwide
  Test: pick two universities worldwide and we can show they are connected with fat pipes and a trusted path for resource sharing supported by our interfederation framework
GEANT has also a track record of maintaining this infrastructure and evolve it over time, including adding/replacing protocols used (SAML->OIDC)
GEANT has governance structure so that it can speak in the name of the NREN community and somehow combine the existing national structures into a international structure
GEANT has a track record in doing that on a technical level with the interfederation metadata collection and re-distribution mechanisms in place for long time
GEANT has also a track record in setting up and maintaining the governance for those services (committees for profiles and semantics, security profiles, etc.)
Marina: regroup around the terms “GÉANT project”, “GÉANT organisation” and “GÉANT community”
GEANT is particularly valuable to ”think global scaling”, not just Europe. And we have the global people network to support this.

## Slide 11: Scoping: Scoping: What will our contribution be?
Proposed positioning:
Rather paper than services initially
Propose and validate our positioning towards SSI as a community
Propose engagements on appropriate levels (NRENs, GÉANT, others)
Spin-off activities, most likely elsewhere (e.g. T&I incubator)
Our goal is to produce a report (show first results for 2023 in January and a first version in Q1). There are no specific requirements regarding the format:
we could break the report in chunks and people can focus on the different parts.
For the first version, we use the expertise we have in the group and engage the community for validation after the first version.
The report could have two chapters: strategy and technology, and the work on the link in between them to demonstrate the dependencies.

## Slide 12: Proposed initial work plan
Still in 2023:
  Workshop to discuss (preferably also validate) the scoping of the task (candidate dates based on doodle) -> Christoph to prepare a list of activities to discuss engagements at the meeting
  Kick-off initial research topics as per the description of work:
    “Review existing services to identify opportunities and challenges to adopt the distributed technologies paradigm.” mainly done, reuse existing material
    “Gather previous work done by the NRENs/universities on using SSI technologies, as well as other sectors.” crowdsource among ourselves
  Propose on first outline (TOC) of report in line with other WP5 deliverables (check with Marina)
    first proposal as input to the next workshop (Marina and Christoph)
    Idea: two sections “strategy” and “technical” plus implications of choices in either section to the other
In 2024:
  Continue to work on report
    first report needed in Q1 (format up to us), validate and reiterate later
  Fill backlog for activities to pick up later
    We might re-use the format of the TF-DLT to engage a larger community to discuss and stay informed about developments in the area of distributed identities
    For issues on the policy/governance layer infoshares are more appropriate

## Slide 13: Our tooling for collaboration
Mailing list for info sharing and collaboration in Task: gn5-1-wp5-t7@lists.geant.org
Intranet: https://geantprojects.sharepoint.com/sites/gn5-1
  Project templates: https://geantprojects.sharepoint.com/sites/gn5-1/SitePages/Templates.aspx
  Onboarding guidance: https://wiki.geant.org/display/GW/GN5-1+and+GN5-IC1+Onboarding+Presentations+and+Guidance
  WP5: https://wiki.geant.org/display/GWP5/GN5+Trust+Identity
  WP5 T7: https://wiki.geant.org/display/GWP5/T7+-+Distributed+Identities
These Slides: https://wiki.geant.org/display/GWP5/Task+meetings
Zoom offering by GEANT, if needed
Offering by GEANT exists to support physical meetings

## Slide 14: Administrivia
GN5-1 particularities:
  Familiar with your organisational accounting processes for time spent in this task? Aware of what your organisation agreed in terms of FTEs for 2023 and 2024?
  If not, we will take this up shortly (either as group or individually, after checking your needs)
  (editor note: sorry, most of this does not apply for me the same way…)
Known vacation plans?
  Christoph to check the options within our Confluence space
Budget:
  Christoph to come up with a break-down of activities as input for the next meeting to adjust and validate.
  Then the group members can apply for activities with effort estimates they are willing and able to contribute.
  Marina will subsequently “fix” the budget with an appropriate change request (enough leeway is likely available)

## Slide 15: Next steps and tasks
Set up bi-weeklies (Monday afternoon like this time? Doodle needed?)
  We go for Wed mornings, 10h-11h, starting 3 Jan 2024
Set up scoping workshop (looked promising in the poll: 20 Dec?)
  Repurposed to planning workshop with activity list as input
  We go for 20 Dec, 9h-11h
Report TOC and check with other dependencies with Marina
  Christoph to check with Marina for the break-down of activities before workshop
Call for volunteers for the research topics as per the DoW: repurposed to set of activities to pick and choose and to apply for
  Review existing services to identify opportunities and challenges to adopt the distributed technologies paradigm. Grab existing results as a start
  Gather previous work done by the NRENs/universities on using SSI technologies, as well as other sectors. Croud-source among ourselves

## Slide 16: Thank You